## Summary
POKROV Web App Feature/User Story Tracker
Canonical tracker for source-code-derived webapp user stories, defects, test runs, and route inventory. Update this workbook after each test/fix/retest pass.
Metric | Value |  | Story status | Count | Defect status | Count
Total user stories |  |  | Ready for test |  | Open - needs verification
Defect rows logged |  |  | Tested pass |  | Open
Open/suspected defects |  |  | Defect found |  | Fixed - needs retest
Test runs logged |  |  | Fixed - needs retest |  | Retested pass
|  |  | Retested pass |  | Blocked by access
|  |  | Blocked by access |  | Closed - not a defect
Phase | Status | Owner | Last update | Notes
Inventory | Completed | Codex | 2026-06-26 | Routes, components, APIs, route inventory, source notes, and 58 user stories recorded.
Testing | Completed | Codex | 2026-06-26 | All available webapp e2e specs run; defects and logistics errors logged.
Fixing | Completed | Codex | 2026-06-26 | Email readiness gates, manual setup hash behavior, OIDC label expectation, and Telegram script test stub fixed.
Retesting | Completed | Codex | 2026-06-26 | Build plus settings, OIDC/Telegram, cabinet, and admin specs passed after fixes.
Canonical file | This workbook | Codex | 2026-06-26 | C:\Users\kiwun\Documents\ai\VPN\docs\developer\webapp-feature-user-stories.xlsx
Source of truth | Code + canon docs | Repo | 2026-06-26 | AGENTS.md, docs/README.md, product, architecture, operations, developer guide, repository map, and webapp/README.md.

## User Stories
Story ID | Surface | Route | Role | Feature | User Story | Expected Behavior From Code | Primary Source | API/Contracts | Canon Guardrails | Current Coverage | Story Status | Test Method | Latest Result | Defect IDs | Fix Status | Retest Status | Notes
WEB-001 | Cabinet auth | / | Visitor | Root cabinet entry | As a visitor, I can land on the POKROV cabinet entry and understand that Telegram and approved email auth are the entry paths. | The root page shows POKROV cabinet branding, a return-to-site link, Telegram entry, and email entry only when the email delivery gate is public-ready. | webapp/src/app/page.tsx; webapp/src/components/cabinet-entry-auth.tsx | /api/auth/email/status; /api/auth/email/*; Telegram widget/OIDC | App-first identity; public email forms must be gated by delivery readiness. | E2E exists: cabinet-flow, settings-email-link | Retested pass | Playwright cabinet/settings/auth specs; source-code user-story audit. | PASS 2026-06-26: cabinet-flow (27/27), settings-email-link (6/6), oidc-fallback + telegram-login-refresh (7/7) where applicable. | D-001; D-005 | Fixed | Passed 2026-06-26 | Email entry now renders only after the public-ready email status gate; Telegram remains available.
WEB-002 | Cabinet auth | /?cabinet_handoff=... | App user | App handoff exchange | As an app user, I can open a one-time cabinet handoff link and land on the intended cabinet route. | The handoff token is exchanged once, stored as a web session, removed from the URL, and the API-provided target path is honored. | webapp/src/lib/session.tsx; webapp/src/lib/api.ts | /api/auth/cabinet-handoff/exchange; localStorage portal_web_session_token | Startup update is explicit; app-first session continuity must avoid leaking tokens in URLs. | E2E exists: cabinet-flow | Retested pass | Playwright cabinet/settings/auth specs; source-code user-story audit. | PASS 2026-06-26: cabinet-flow (27/27), settings-email-link (6/6), oidc-fallback + telegram-login-refresh (7/7) where applicable. |  | No fix needed | Passed 2026-06-26
WEB-003 | Cabinet auth | / | Returning user | Web session reuse | As a returning user, I can reopen the cabinet without seeing the auth entry again when a valid web session exists. | The provider reads localStorage/cookie/URL session token, fetches auth session, dashboard, and user, then redirects to /dashboard/. | webapp/src/lib/session.tsx; webapp/src/app/page.tsx | /api/auth/session; /api/dashboard; /api/user/{id} | Automatic username/session sync is primary; stale sessions must degrade safely. | E2E exists: cabinet-flow | Retested pass | Playwright cabinet/settings/auth specs; source-code user-story audit. | PASS 2026-06-26: cabinet-flow (27/27), settings-email-link (6/6), oidc-fallback + telegram-login-refresh (7/7) where applicable. |  | No fix needed | Passed 2026-06-26
WEB-004 | Cabinet auth | all protected routes | User | Expired session recovery | As a user with an expired session, I get a human reauth path instead of raw API errors. | Telegram deprecated/session errors and auth failures map to a reauth CTA with retry, switch-account, and support options. | webapp/src/lib/session.tsx; webapp/src/components/cabinet-shell.tsx | /api/auth/session; Telegram auth errors | Do not expose raw technical failures to users. | E2E exists: cabinet-flow, telegram-login-refresh | Retested pass | Playwright cabinet/settings/auth specs; source-code user-story audit. | PASS 2026-06-26: cabinet-flow (27/27), settings-email-link (6/6), oidc-fallback + telegram-login-refresh (7/7) where applicable. |  | No fix needed | Passed 2026-06-26
WEB-005 | Cabinet auth | / | Visitor | Telegram login | As a visitor, I can sign in with Telegram through the widget or OIDC fallback. | Fresh widget payloads are accepted, stale payloads are blocked locally, and OIDC start can fall back to canonical API when app origin returns HTML. | webapp/src/components/telegram-login-widget.tsx; webapp/src/lib/api.ts; webapp/src/lib/telegram-auth.ts | /api/auth/telegram; /api/auth/telegram/oidc/start; /api/auth/telegram/oidc/finish | Main bot is @pokrov_vpnbot; auth errors should be reauth-friendly. | E2E exists: telegram-login-refresh, oidc-fallback | Retested pass | Playwright cabinet/settings/auth specs; source-code user-story audit. | PASS 2026-06-26: cabinet-flow (27/27), settings-email-link (6/6), oidc-fallback + telegram-login-refresh (7/7) where applicable. | D-004 | Fixed | Passed 2026-06-26 | OIDC fallback test now targets the current Telegram CTA label.
WEB-006 | Cabinet auth | /verify; /recover | Email user | Email verify/recovery bridge | As an email user, I can open relay verification or recovery links and continue in the root auth screen. | The /verify and /recover bridge routes redirect token params into root query params, clear prior sessions, prefill the correct token field, and remove token params from the URL. | webapp/src/app/verify/page.tsx; webapp/src/app/recover/page.tsx; webapp/src/components/cabinet-entry-auth.tsx | /api/auth/email/verify; /api/auth/email/recover/finish | Email auth must remain gated by delivery readiness and separate verify/recovery tokens. | E2E exists: settings-email-link | Retested pass | Playwright cabinet/settings/auth specs; source-code user-story audit. | PASS 2026-06-26: cabinet-flow (27/27), settings-email-link (6/6), oidc-fallback + telegram-login-refresh (7/7) where applicable. |  | No fix needed | Passed 2026-06-26
WEB-007 | Cabinet shell | /dashboard/ and dashboard group | Cabinet user | Responsive cabinet shell | As a cabinet user, I can navigate the main app on desktop and mobile without losing context. | Desktop uses sidebar/top shell; mobile uses compact header and bottom nav; active route, theme toggle, marketing link, logout, and admin link for admins remain usable. | webapp/src/components/cabinet-shell.tsx; webapp/src/components/app-route-link.tsx | Session provider state | Cabinet is continuation-first, not a landing page. | E2E exists: cabinet-flow | Retested pass | Playwright cabinet/settings/auth specs; source-code user-story audit. | PASS 2026-06-26: cabinet-flow (27/27), settings-email-link (6/6), oidc-fallback + telegram-login-refresh (7/7) where applicable. |  | No fix needed | Passed 2026-06-26
WEB-008 | Cabinet shell | not-found/error | Cabinet user | Recovery screens | As a cabinet user, I get branded recovery screens when a route or render path fails. | Not-found and error surfaces keep POKROV branding and offer routes back to dashboard/site/support instead of a blank failure. | webapp/src/app/not-found.tsx; webapp/src/app/error.tsx; webapp/src/app/(admin)/not-found.tsx; webapp/src/app/(admin)/error.tsx | Client routing | User recovery should be compact and honest. | E2E exists: cabinet-flow | Retested pass | Playwright cabinet/settings/auth specs; source-code user-story audit. | PASS 2026-06-26: cabinet-flow (27/27), settings-email-link (6/6), oidc-fallback + telegram-login-refresh (7/7) where applicable. |  | No fix needed | Passed 2026-06-26
WEB-009 | Dashboard | /dashboard/ | Cabinet user | Access status summary | As a user, I can see whether access is active, trial, soft-limited, or expired and what to do next. | Dashboard status chooses the correct message and action for inactive, soft mode, trial, and active accounts. | webapp/src/app/(dashboard)/dashboard/page.tsx | /api/dashboard; /api/user/{id} | Consumer-safe access actions; no raw config links on first layer. | E2E exists: cabinet-flow | Retested pass | Playwright cabinet/settings/auth specs; source-code user-story audit. | PASS 2026-06-26: cabinet-flow (27/27), settings-email-link (6/6), oidc-fallback + telegram-login-refresh (7/7) where applicable. |  | No fix needed | Passed 2026-06-26
WEB-010 | Dashboard | /dashboard/ | Cabinet user | Summary cards and recent devices | As a user, I can scan traffic, device, connection, and expiry status without seeing node internals. | Dashboard renders compact tiles, quick actions to redeem/support, and up to two recent devices. | webapp/src/app/(dashboard)/dashboard/page.tsx | /api/dashboard; /api/user/{id} | Public config URL hidden by default; safe summaries only. | E2E exists: cabinet-flow | Retested pass | Playwright cabinet/settings/auth specs; source-code user-story audit. | PASS 2026-06-26: cabinet-flow (27/27), settings-email-link (6/6), oidc-fallback + telegram-login-refresh (7/7) where applicable. |  | No fix needed | Passed 2026-06-26
WEB-011 | Downloads | /downloads/; /dashboard/downloads/ | Cabinet user | Client downloads | As a user, I can download the correct Android or Windows beta artifact and see install caveats. | The surface reads /api/client/apps, prioritizes Android split APKs and Windows EXE/ZIP, shows updated dates, warns about unsigned Windows, and degrades to support if links are unavailable; legacy /dashboard/downloads redirects. | webapp/src/components/cabinet/downloads-surface.tsx; webapp/src/app/(dashboard)/downloads/page.tsx; webapp/src/app/(dashboard)/dashboard/downloads/page.tsx | /api/client/apps | Public binaries come from GitHub Releases; do not claim store/trusted signing. | E2E exists: cabinet-flow | Retested pass | Playwright cabinet/settings/auth specs; source-code user-story audit. | PASS 2026-06-26: cabinet-flow (27/27), settings-email-link (6/6), oidc-fallback + telegram-login-refresh (7/7) where applicable. |  | No fix needed | Passed 2026-06-26
WEB-012 | Subscription | /subscription/; /pricing/ | Cabinet user | Plan list | As a user, I can review available plans and continue to payment from the cabinet. | Plans load from public API with shared fallback, paid/current/featured states are shown, and /pricing redirects to /subscription. | webapp/src/app/(dashboard)/subscription/page.tsx; webapp/src/app/pricing/page.tsx | /api/public/plans; shared/product-facts | Checkout is continuation-only; no unsupported release/payment claims. | E2E exists: cabinet-flow | Retested pass | Playwright cabinet/settings/auth specs; source-code user-story audit. | PASS 2026-06-26: cabinet-flow (27/27), settings-email-link (6/6), oidc-fallback + telegram-login-refresh (7/7) where applicable. |  | No fix needed | Passed 2026-06-26
WEB-013 | Subscription | /subscription/#manual-setup | Cabinet user | Manual connection fallback | As a user, I can reveal a raw connection link/QR only when I explicitly need manual setup and the account has an active link. | The manual setup panel remains hidden until requested, requires an active subscription URL, displays QR/copy/open actions only when ready, and keeps it framed as recovery. | webapp/src/app/(dashboard)/subscription/page.tsx | subscription_url from /api/dashboard and /api/user/{id} | Connect host can appear only in explicit manual/recovery fallback. | E2E exists: cabinet-flow | Retested pass | Playwright cabinet/settings/auth specs; source-code user-story audit. | PASS 2026-06-26: cabinet-flow (27/27), settings-email-link (6/6), oidc-fallback + telegram-login-refresh (7/7) where applicable. | D-003 | Fixed | Passed 2026-06-26 | Direct #manual-setup entry stays closed until an active subscription URL exists.
WEB-014 | Checkout | /subscription/checkout/ | Paying user | RUB checkout continuation | As a paying user, I can choose SBP or card and continue to the Lava-backed checkout for the supported start plan. | Checkout filters to start_99, loads providers, applies local promo preview, creates a RUB order with selected method/provider, and redirects to payment_url; blocked providers show an unavailable notice. | webapp/src/app/(dashboard)/subscription/checkout/page.tsx | /api/public/catalog; /api/payments/rub/providers; /api/payments/rub/checkout | Lava.top beta proof only; no silent fulfillment or unsupported payment maturity claims. | E2E exists: cabinet-flow | Retested pass | Playwright cabinet/settings/auth specs; source-code user-story audit. | PASS 2026-06-26: cabinet-flow (27/27), settings-email-link (6/6), oidc-fallback + telegram-login-refresh (7/7) where applicable. |  | No fix needed | Passed 2026-06-26
WEB-015 | Redeem | /redeem/ | Cabinet user | Activation code redeem | As a user, I can check and redeem an access key or gift code, and I am protected from pasting a connection link by mistake. | The form normalizes keys, rejects URL/connection-link input with a useful message, looks up status, redeems valid keys, refreshes session, and surfaces next actions. | webapp/src/app/(dashboard)/redeem/page.tsx | /api/access-keys/status/{key}; /api/access-keys/redeem; promo/gift APIs | Raw subscription links are recovery artifacts, not activation codes. | E2E exists: cabinet-flow | Retested pass | Playwright cabinet/settings/auth specs; source-code user-story audit. | PASS 2026-06-26: cabinet-flow (27/27), settings-email-link (6/6), oidc-fallback + telegram-login-refresh (7/7) where applicable. |  | No fix needed | Passed 2026-06-26
WEB-016 | Devices | /devices/ | Cabinet user | Device and runtime connection view | As a user, I can see my devices and current runtime connection counts in a user-safe way. | Devices page shows device counts, active connections/users, active/known nodes, a device list or empty state, and actions to downloads/subscription/support. | webapp/src/app/(dashboard)/devices/page.tsx | /api/user/{id}; /api/dashboard | No raw node secrets or config payloads in user-facing pages. | E2E exists: cabinet-flow | Retested pass | Playwright cabinet/settings/auth specs; source-code user-story audit. | PASS 2026-06-26: cabinet-flow (27/27), settings-email-link (6/6), oidc-fallback + telegram-login-refresh (7/7) where applicable. |  | No fix needed | Passed 2026-06-26
WEB-017 | Statistics | /statistics/ | Cabinet user | Safe usage statistics | As a user, I can see usage and connection summary without operator-only node details. | Statistics page renders access mode, traffic, devices, active connections/users, active/known nodes, reset date, and support/subscription/download actions. | webapp/src/app/(dashboard)/statistics/page.tsx | /api/dashboard; /api/user/{id} | Missing runtime data must not look like authoritative zero. | E2E exists: cabinet-flow | Retested pass | Playwright cabinet/settings/auth specs; source-code user-story audit. | PASS 2026-06-26: cabinet-flow (27/27), settings-email-link (6/6), oidc-fallback + telegram-login-refresh (7/7) where applicable. |  | No fix needed | Passed 2026-06-26
WEB-018 | Settings | /settings/; /profile/ | Cabinet user | Profile and identity settings | As a user, I can view profile identity state and use compatibility redirects without raw account internals. | Settings shows profile, linked Telegram/email state, safe identifiers, and /profile redirects to /settings. | webapp/src/app/(dashboard)/settings/page.tsx; webapp/src/app/(dashboard)/profile/page.tsx | /api/auth/session; /api/user/{id} | App-first identity; manual sync is recovery only. | E2E exists: settings-email-link | Retested pass | Playwright cabinet/settings/auth specs; source-code user-story audit. | PASS 2026-06-26: cabinet-flow (27/27), settings-email-link (6/6), oidc-fallback + telegram-login-refresh (7/7) where applicable. |  | No fix needed | Passed 2026-06-26
WEB-019 | Settings | /settings/#email-link | Cabinet user | Email linking | As a Telegram-linked user, I can attach email login to the same account when email auth is public-ready. | Settings registers email with current bearer auth, clears password after send, verifies the token, stores returned web session, and refreshes identity. | webapp/src/app/(dashboard)/settings/page.tsx | /api/auth/email/status; /api/auth/email/register; /api/auth/email/verify | Public email forms must be gated by delivery readiness. | E2E exists: settings-email-link | Retested pass | Playwright cabinet/settings/auth specs; source-code user-story audit. | PASS 2026-06-26: cabinet-flow (27/27), settings-email-link (6/6), oidc-fallback + telegram-login-refresh (7/7) where applicable. | D-002; D-005 | Fixed | Passed 2026-06-26 | Settings email linking now uses the same public-ready email status gate as root auth.
WEB-020 | Settings | /settings/ | Email-only user | Telegram linking | As an email-only user, I can start Telegram linking and open the bot link from settings. | The page calls /api/client/telegram/link, shows bot instructions and a bot_url when linking is not complete, and shows support if already linked. | webapp/src/app/(dashboard)/settings/page.tsx | /api/client/telegram/link | Main bot is @pokrov_vpnbot; Telegram admin is fallback-only. | E2E exists: settings-email-link | Retested pass | Playwright cabinet/settings/auth specs; source-code user-story audit. | PASS 2026-06-26: cabinet-flow (27/27), settings-email-link (6/6), oidc-fallback + telegram-login-refresh (7/7) where applicable. | D-005 | Fixed | Passed 2026-06-26 | Settings Telegram linking test stubs the external Telegram WebApp script deterministically.
WEB-021 | Settings | /settings/ | Cabinet user | Telegram channel bonus | As a user, I can check channel subscription status and claim the +10 day Telegram reward when eligible. | Settings links @pokrov_vpn, checks subscriber status, disables already-claimed/unverified cases, and claims bonus through the backend. | webapp/src/app/(dashboard)/settings/page.tsx | /api/channel/subscriber/check; /api/bonuses/channel/claim | Telegram reward is +10 days; public channel is @pokrov_vpn. | E2E exists: cabinet-flow | Retested pass | Playwright cabinet/settings/auth specs; source-code user-story audit. | PASS 2026-06-26: cabinet-flow (27/27), settings-email-link (6/6), oidc-fallback + telegram-login-refresh (7/7) where applicable. |  | No fix needed | Passed 2026-06-26
WEB-022 | Support | /support/ | Cabinet user | Ticket list and creation | As a user, I can view support tickets and create a categorized ticket with optional attachment. | Support loads ticket queue, shows latest/open counts, offers category presets, validates body, uploads attachment when present, creates a ticket, reloads tickets, and keeps Telegram support as fallback. | webapp/src/app/(dashboard)/support/page.tsx | /api/tickets; /api/tickets/attachments; /api/tickets/create | Support is async ticket lifecycle, not fake live chat. | E2E exists: cabinet-flow | Retested pass | Playwright cabinet/settings/auth specs; source-code user-story audit. | PASS 2026-06-26: cabinet-flow (27/27), settings-email-link (6/6), oidc-fallback + telegram-login-refresh (7/7) where applicable. |  | No fix needed | Passed 2026-06-26
WEB-023 | Support | /support/thread/?id= | Cabinet user | Ticket thread | As a user, I can read a support thread, view safe attachments, and reply while the ticket is open. | Thread requires id, loads ticket details, renders user/admin/AI messages and safe attachments, allows reply/upload only when not closed, and shows not-found/error states. | webapp/src/app/(dashboard)/support/thread/page.tsx | /api/tickets/{id}; /api/tickets/{id}/messages; /api/tickets/attachments | Do not expose private access data in support attachments. | E2E exists: cabinet-flow | Retested pass | Playwright cabinet/settings/auth specs; source-code user-story audit. | PASS 2026-06-26: cabinet-flow (27/27), settings-email-link (6/6), oidc-fallback + telegram-login-refresh (7/7) where applicable. |  | No fix needed | Passed 2026-06-26
WEB-024 | Support | /support/legal/ | Cabinet user | Legal support links | As a user, I can reach compact offer and privacy links from support without leaving the cabinet confused. | Legal page links to marketing offer/privacy URLs and offers support/subscription actions. | webapp/src/app/(dashboard)/support/legal/page.tsx | shared public URLs | Legal and payment claims must stay evidence-backed. | E2E exists: cabinet-flow | Retested pass | Playwright cabinet/settings/auth specs; source-code user-story audit. | PASS 2026-06-26: cabinet-flow (27/27), settings-email-link (6/6), oidc-fallback + telegram-login-refresh (7/7) where applicable. |  | No fix needed | Passed 2026-06-26
ADM-001 | Admin shell | /admin/* | Operator | Admin gate | As a non-admin, I cannot access admin routes; as an admin, I can open the guarded operator surface. | Admin layout fetches session/user, redirects non-admins to /dashboard/, renders admin children only for admins, and /admin redirects to /admin/dashboard. | webapp/src/app/(admin)/admin/layout.tsx; webapp/src/app/(admin)/admin/page.tsx | /api/auth/session; /api/user/{id}; /api/admin/summary | Web admin is the primary operator surface; Telegram admin is fallback-only. | E2E exists: admin-gate | Retested pass | Playwright admin-gate; source-code user-story audit. | PASS 2026-06-26: npx.cmd playwright test e2e/admin-gate.spec.ts (19/19). |  | No fix needed | Passed 2026-06-26
ADM-002 | Admin shell | /admin/* | Operator | Grouped navigation and attention counts | As an operator, I can scan admin sections by operational group and see attention badges without leaving the surface. | Sidebar groups diagnostics, people, access, payments, network, messaging, feedback; attention counts come from admin summary; topbar links back to cabinet and logout. | webapp/src/app/(admin)/admin/layout.tsx; webapp/src/app/(admin)/admin/nav.ts | /api/admin/summary | Admin surface is primary; support/payment/node counters must not fake data. | E2E exists: admin-gate | Retested pass | Playwright admin-gate; source-code user-story audit. | PASS 2026-06-26: npx.cmd playwright test e2e/admin-gate.spec.ts (19/19). |  | No fix needed | Passed 2026-06-26
ADM-003 | Admin dashboard | /admin/dashboard | Operator | Operator shift dashboard | As an operator, I can see current operational health, queues, and recent people/tickets/network context on one screen. | Dashboard loads summary, metrics, time series, users, tickets, and WARP summary; shows stale metrics/unhealthy nodes/payment/ticket warnings, queue cards, week context, people, tickets, and network widgets. | webapp/src/app/(admin)/admin/dashboard/page.tsx; webapp/src/components/admin/dashboard/dashboard-widgets.tsx | /api/admin/summary; /api/admin/metrics/status; /api/admin/metrics/timeseries; /api/admin/users; /api/admin/tickets; /api/admin/client/warp/summary | Missing data must not render as real zero. | E2E exists: admin-gate | Retested pass | Playwright admin-gate; source-code user-story audit. | PASS 2026-06-26: npx.cmd playwright test e2e/admin-gate.spec.ts (19/19). |  | No fix needed | Passed 2026-06-26
ADM-004 | Admin diagnostics | /admin/funnel | Operator | Funnel diagnostics | As an operator, I can inspect conversion stages and drop reasons over preset ranges. | Funnel page switches 7/14/30 day range, loads summary, shows totals, stage conversion/drop, source breakdown, recent events, and refresh/error states. | webapp/src/app/(admin)/admin/funnel/page.tsx | /api/admin/funnel/summary | Telemetry is diagnostic; no unsupported conversion claims. | E2E exists: admin-gate opens route | Retested pass | Playwright admin-gate; source-code user-story audit. | PASS 2026-06-26: npx.cmd playwright test e2e/admin-gate.spec.ts (19/19). |  | No fix needed | Passed 2026-06-26
ADM-005 | Admin release | /admin/release | Operator | Release cockpit | As an operator, I can see beta release gates and safe public claims without confusing beta with stable/store readiness. | Release cockpit combines runtime apps/email/metrics/payments with release-status artifact gates, shows GO/NO-GO, safe vs unsafe claims, and copyable operator commands. | webapp/src/app/(admin)/admin/release/page.tsx | /api/client/apps; /api/auth/email/status; /api/admin/metrics/status; /api/payments/rub/providers; /release-status.json | Do not claim stores, trusted signing, stable 1.0.0, raw Android physical proof, or RU readiness without evidence. | E2E exists: admin-gate | Retested pass | Playwright admin-gate; source-code user-story audit. | PASS 2026-06-26: npx.cmd playwright test e2e/admin-gate.spec.ts (19/19). |  | No fix needed | Passed 2026-06-26
ADM-006 | Admin users | /admin/users | Operator | Users search/filter/sort/pagination | As an operator, I can find users through URL-synced filters and stable table pagination. | Users page reads query params, loads users, syncs filter state into URL, supports search/status/origin/observer/sort/page, and preserves selection when possible. | webapp/src/app/(admin)/admin/users/page.tsx; webapp/src/components/admin/users/* | /api/admin/users | Operator lists must distinguish runtime vs entitlement truth. | E2E exists: admin-gate | Retested pass | Playwright admin-gate; source-code user-story audit. | PASS 2026-06-26: npx.cmd playwright test e2e/admin-gate.spec.ts (19/19). |  | No fix needed | Passed 2026-06-26
ADM-007 | Admin users | /admin/users | Operator | User detail diagnostics | As an operator, I can inspect a selected user without losing safe operational context. | Side panel shows overview, observer-lite badges, identities, subscription URL/token copy, payments, key history, audit history, and reload actions. | webapp/src/components/admin/users/admin-user-side-panel.tsx; admin-user-overview-view.tsx; admin-user-history-views.tsx | /api/admin/users/{tg_id}; /api/admin/audit; /api/admin/users/{tg_id}/keys/history | Private values are operator-only and stay inside admin. | E2E exists: admin-gate | Retested pass | Playwright admin-gate; source-code user-story audit. | PASS 2026-06-26: npx.cmd playwright test e2e/admin-gate.spec.ts (19/19). |  | No fix needed | Passed 2026-06-26
ADM-008 | Admin users | /admin/users | Operator | Direct user message | As an operator, I can send a targeted message to a selected user with an explicit dialog. | Message dialog requires non-empty text, calls admin user message API, closes on success, reloads selected card, and reports errors. | webapp/src/app/(admin)/admin/users/page.tsx | /api/admin/users/{tg_id}/message | Messaging must be explicit operator action. | Code inventory | Retested pass | Playwright admin-gate; source-code user-story audit. | PASS 2026-06-26: npx.cmd playwright test e2e/admin-gate.spec.ts (19/19). |  | No fix needed | Passed 2026-06-26
ADM-009 | Admin users | /admin/users | Operator | Manual access controls | As an operator, I can extend, block/unblock, or regenerate a selected user's token with explicit feedback. | Extend validates positive days; block toggles status; token regeneration opens a copyable subscription URL and notes panel sync state; list and detail reload after changes. | webapp/src/app/(admin)/admin/users/page.tsx | /api/admin/users/{tg_id}/extend; /block; /regenerate-token | Manual sync is compatibility/recovery; panel sync status must be honest. | Code inventory | Retested pass | Playwright admin-gate; source-code user-story audit. | PASS 2026-06-26: npx.cmd playwright test e2e/admin-gate.spec.ts (19/19). |  | No fix needed | Passed 2026-06-26
ADM-010 | Admin users | /admin/users | Operator | Safe delete manual/test user | As an operator, I can delete only manual/test accounts and cannot delete real users by accident. | Delete button only appears for manual/test-like users; confirmation dialog calls safe delete API, clears selection, and reloads users. | webapp/src/app/(admin)/admin/users/page.tsx; webapp/src/components/admin/users/admin-users-format.ts | /api/admin/users/{tg_id}/delete-test | Destructive safe-delete only manual/test users. | E2E exists: admin-gate | Retested pass | Playwright admin-gate; source-code user-story audit. | PASS 2026-06-26: npx.cmd playwright test e2e/admin-gate.spec.ts (19/19). |  | No fix needed | Passed 2026-06-26
ADM-011 | Admin users | /admin/users | Operator | Create manual test account | As an operator, I can create a manual test user with a display name and access days. | Create dialog validates display name and positive days, calls manual create, closes, and reloads users. | webapp/src/app/(admin)/admin/users/page.tsx | /api/admin/users/manual | Manual/test accounts must stay distinguishable from real users. | Code inventory | Retested pass | Playwright admin-gate; source-code user-story audit. | PASS 2026-06-26: npx.cmd playwright test e2e/admin-gate.spec.ts (19/19). |  | No fix needed | Passed 2026-06-26
ADM-012 | Admin users | /admin/users | Operator | Per-node key actions | As an operator, I can toggle, reset traffic, or resync a selected user's key for a specific node. | Key policy editor disables while busy, runs node-specific action, reports success, and reloads selected details. | webapp/src/components/admin/users/admin-user-key-policy-editor.tsx; webapp/src/app/(admin)/admin/users/page.tsx | /api/admin/users/{tg_id}/keys/{node}/toggle; /reset-traffic; /resync-sub-id | Node assignment changes must not override canonical pool rules. | Code inventory | Retested pass | Playwright admin-gate; source-code user-story audit. | PASS 2026-06-26: npx.cmd playwright test e2e/admin-gate.spec.ts (19/19). |  | No fix needed | Passed 2026-06-26
ADM-013 | Admin users | /admin/users | Operator | Per-node key policy editor | As an operator, I can edit per-node key limits and flags for a selected user. | Policy draft fields parse nullable numeric limits, enabled flags, and metadata, save to key limit API, and reload selected details. | webapp/src/components/admin/users/admin-user-key-policy-editor.tsx; webapp/src/app/(admin)/admin/users/page.tsx | /api/admin/users/{tg_id}/keys/{node}/limits | Runtime and entitlement truth are separate. | Code inventory | Retested pass | Playwright admin-gate; source-code user-story audit. | PASS 2026-06-26: npx.cmd playwright test e2e/admin-gate.spec.ts (19/19). |  | No fix needed | Passed 2026-06-26
ADM-014 | Admin users | /admin/users | Operator | Preset actions | As an operator, I can run common user presets without scripting. | Preset buttons run reset_key, rotate_link, extend_1d, or send_guide; success reports changed/failed counts and opens token dialog when relevant. | webapp/src/components/admin/users/admin-user-side-panel.tsx; webapp/src/app/(admin)/admin/users/page.tsx | /api/admin/users/{tg_id}/presets/{preset} | Preset results must report sync uncertainty honestly. | Code inventory | Retested pass | Playwright admin-gate; source-code user-story audit. | PASS 2026-06-26: npx.cmd playwright test e2e/admin-gate.spec.ts (19/19). |  | No fix needed | Passed 2026-06-26
ADM-015 | Admin users | /admin/users | Operator | Bulk key action with dry-run | As an operator, I can prepare bulk key actions, inspect dry-run output, and confirm deliberately. | Bulk action panel captures segment/action/days/node/speed/limits/flags, first opens confirm/dry-run path unless forced, then reports changed/failed totals and reloads selected card. | webapp/src/app/(admin)/admin/users/page.tsx; webapp/src/components/admin/users/admin-users-query-panel.tsx | /api/admin/users/bulk-key-action | Mass actions require explicit review before changes. | Code inventory | Retested pass | Playwright admin-gate; source-code user-story audit. | PASS 2026-06-26: npx.cmd playwright test e2e/admin-gate.spec.ts (19/19). |  | No fix needed | Passed 2026-06-26
ADM-016 | Admin bonuses | /admin/bonuses | Operator | Wheel configuration | As an operator, I can review and update bonus wheel weights and presets. | Bonuses page loads wheel config, edits preset/cooldown/weights JSON, saves through API, and reloads with success/error feedback. | webapp/src/app/(admin)/admin/bonuses/page.tsx | /api/admin/wheel-config | Dynamic content cannot alter routing/security behavior without policy. | E2E opens route | Retested pass | Playwright admin-gate; source-code user-story audit. | PASS 2026-06-26: npx.cmd playwright test e2e/admin-gate.spec.ts (19/19). |  | No fix needed | Passed 2026-06-26
ADM-017 | Admin bonuses | /admin/bonuses | Operator | Loyalty config and grant | As an operator, I can edit loyalty configuration and grant a loyalty reward to a user. | Bonuses page edits loyalty JSON, saves config, validates tg_id/tier days, grants reward, and reports sync state. | webapp/src/app/(admin)/admin/bonuses/page.tsx | /api/admin/loyalty/config; /api/admin/users/{tg_id}/loyalty/grant | Trial/reward days must match canon and sync honesty. | Code inventory | Retested pass | Playwright admin-gate; source-code user-story audit. | PASS 2026-06-26: npx.cmd playwright test e2e/admin-gate.spec.ts (19/19). |  | No fix needed | Passed 2026-06-26
ADM-018 | Admin referrals | /admin/referrals | Operator | Start links | As an operator, I can create, edit, deactivate, and open bot start links. | Referrals page loads active start links, opens create/edit/delete dialogs, persists code/description/target/is_active, and reloads results. | webapp/src/app/(admin)/admin/referrals/page.tsx | /api/admin/start-links | Main bot is @pokrov_vpnbot; start links must be explicit operator assets. | E2E opens route | Retested pass | Playwright admin-gate; source-code user-story audit. | PASS 2026-06-26: npx.cmd playwright test e2e/admin-gate.spec.ts (19/19). |  | No fix needed | Passed 2026-06-26
ADM-019 | Admin referrals | /admin/referrals | Operator | Campaign link builder | As an operator, I can generate campaign checkout/bot links and copy them. | Builder accepts promo code, campaign key, and plan code, calls campaign link build API, renders returned values, and copies individual links. | webapp/src/app/(admin)/admin/referrals/page.tsx | /api/admin/campaign-links/build | No unsupported campaign/payment claims. | Code inventory | Retested pass | Playwright admin-gate; source-code user-story audit. | PASS 2026-06-26: npx.cmd playwright test e2e/admin-gate.spec.ts (19/19). |  | No fix needed | Passed 2026-06-26
ADM-020 | Admin referrals | /admin/referrals | Operator | Referral queue processing | As an operator, I can process referral rewards with normal or forced-without-activity modes. | Queue filter loads referral queue; process buttons call API with limit and force flag, report rewarded/waiting/rejected/processed totals, and reload. | webapp/src/app/(admin)/admin/referrals/page.tsx | /api/admin/referrals/queue; /api/admin/referrals/process | Rewards must be auditable and not silently granted. | Code inventory | Retested pass | Playwright admin-gate; source-code user-story audit. | PASS 2026-06-26: npx.cmd playwright test e2e/admin-gate.spec.ts (19/19). |  | No fix needed | Passed 2026-06-26
ADM-021 | Admin promos | /admin/promos | Operator | Access key issuing | As an operator, I can issue access keys for a selected plan and quantity. | Promos page validates plan/quantity, calls issue API, lists issued keys with plan/date, and copies keys. | webapp/src/app/(admin)/admin/promos/page.tsx | /api/admin/access-keys/issue | Promo and gift access must not imply unsupported payment/store claims. | E2E exists: admin-gate | Retested pass | Playwright admin-gate; source-code user-story audit. | PASS 2026-06-26: npx.cmd playwright test e2e/admin-gate.spec.ts (19/19). |  | No fix needed | Passed 2026-06-26
ADM-022 | Admin promos | /admin/promos | Operator | Access key lookup | As an operator, I can look up a key and inspect issued/redeemed status. | Lookup normalizes the key, calls public status API, and shows exists/redeemed/plan/device limit/issued/redeemed dates. | webapp/src/app/(admin)/admin/promos/page.tsx | /api/access-keys/status/{key} | Access-key state should be factual and auditable. | E2E exists: admin-gate | Retested pass | Playwright admin-gate; source-code user-story audit. | PASS 2026-06-26: npx.cmd playwright test e2e/admin-gate.spec.ts (19/19). |  | No fix needed | Passed 2026-06-26
ADM-023 | Admin promos | /admin/promos | Operator | Promo slots | As an operator, I can assign backend-owned promo content to app slots. | Promos page loads remote/fallback catalog, edits slot content/active dates/audience/sort order, and saves assignments. | webapp/src/app/(admin)/admin/promos/page.tsx | /api/admin/promo-slots | Dynamic content is backend-owned JSON only; no arbitrary HTML/JS/tracking. | E2E exists: admin-gate | Retested pass | Playwright admin-gate; source-code user-story audit. | PASS 2026-06-26: npx.cmd playwright test e2e/admin-gate.spec.ts (19/19). |  | No fix needed | Passed 2026-06-26
ADM-024 | Admin payments | /admin/payments | Operator | Payment ledger filters | As an operator, I can filter and search payment orders for reconciliation. | Payments page syncs status/provider/query into URL, loads orders, shows provider/order/user/plan/amount/status/source/events/last callback, and refreshes. | webapp/src/app/(admin)/admin/payments/page.tsx | /api/admin/payments/orders | Payment truth must be evidence-backed. | E2E exists: admin-gate | Retested pass | Playwright admin-gate; source-code user-story audit. | PASS 2026-06-26: npx.cmd playwright test e2e/admin-gate.spec.ts (19/19). |  | No fix needed | Passed 2026-06-26
ADM-025 | Admin payments | /admin/payments | Operator | Manual payment reconciliation | As an operator, I can manually reconcile an order only with an audit note. | Reconcile dialog opens for an order, requires audit note before API call, saves status/note, updates that row, and reports success/errors. | webapp/src/app/(admin)/admin/payments/page.tsx | /api/admin/payments/orders/{provider}/{order_id}/reconcile | Production payment maturity requires reconciliation evidence. | E2E exists: admin-gate | Retested pass | Playwright admin-gate; source-code user-story audit. | PASS 2026-06-26: npx.cmd playwright test e2e/admin-gate.spec.ts (19/19). |  | No fix needed | Passed 2026-06-26
ADM-026 | Admin nodes | /admin/nodes | Operator | Node health and metrics | As an operator, I can inspect node health, metrics freshness, runtime, traffic, and probe failures. | Nodes page loads health, metrics status, 7-day traffic, runtime rows; shows health labels, alert/probe details, panel/dataplane/transport context, and missing-data states. | webapp/src/app/(admin)/admin/nodes/page.tsx | /api/admin/nodes/health; /api/admin/metrics/status; /api/admin/nodes/traffic; /api/admin/nodes/runtime | RU-origin readiness must be distinguished from local/brain checks. | E2E exists: admin-gate | Retested pass | Playwright admin-gate; source-code user-story audit. | PASS 2026-06-26: npx.cmd playwright test e2e/admin-gate.spec.ts (19/19). |  | No fix needed | Passed 2026-06-26
ADM-027 | Admin nodes | /admin/nodes | Operator | Node sync and drift | As an operator, I can run sync for defined segments and inspect panel drift. | Segment buttons call sync with segment/limit, drift button loads drift summary/results, and refresh reloads health/metrics/traffic. | webapp/src/app/(admin)/admin/nodes/page.tsx | /api/admin/nodes/sync; /api/admin/nodes/drift | Node-pool assignments must respect free vs premium canon. | E2E exists: admin-gate opens route | Retested pass | Playwright admin-gate; source-code user-story audit. | PASS 2026-06-26: npx.cmd playwright test e2e/admin-gate.spec.ts (19/19). |  | No fix needed | Passed 2026-06-26
ADM-028 | Admin nodes | /admin/nodes | Operator | Per-node operational actions | As an operator, I can drain, enable, disable, or resync a node from the admin surface. | Action buttons disable while busy, call the matching API, report action notes, reload node data, and disable destructive options when node state disallows them. | webapp/src/app/(admin)/admin/nodes/page.tsx | /api/admin/nodes/{code}/drain; /enable; /disable; /resync | Capacity incidents require node/control-plane telemetry review. | Code inventory | Retested pass | Playwright admin-gate; source-code user-story audit. | PASS 2026-06-26: npx.cmd playwright test e2e/admin-gate.spec.ts (19/19). |  | No fix needed | Passed 2026-06-26
ADM-029 | Admin network | /admin/network | Operator | Network rollout config | As an operator, I can review and save network rollout JSON without losing nested targeting/feed objects. | Network page loads rollout config, renders JSON editor plus summary cards/rules, validates JSON before save, saves through API, and reloads updated config. | webapp/src/app/(admin)/admin/network/page.tsx | /api/admin/network-rollout-config | Ad/filter/routing product work must remain explicit and reversible. | E2E exists: admin-gate | Retested pass | Playwright admin-gate; source-code user-story audit. | PASS 2026-06-26: npx.cmd playwright test e2e/admin-gate.spec.ts (19/19). |  | No fix needed | Passed 2026-06-26
ADM-030 | Admin broadcast | /admin/broadcast | Operator | Broadcast send | As an operator, I can send a targeted or segmented broadcast with explicit limits. | Broadcast page captures segment/limit/tg_ids/text, requires non-empty text, calls broadcast API, and reports sent/skipped/failed totals. | webapp/src/app/(admin)/admin/broadcast/page.tsx | /api/admin/broadcast | Messaging must be explicit and auditable. | E2E opens route | Retested pass | Playwright admin-gate; source-code user-story audit. | PASS 2026-06-26: npx.cmd playwright test e2e/admin-gate.spec.ts (19/19). |  | No fix needed | Passed 2026-06-26
ADM-031 | Admin broadcast | /admin/broadcast | Operator | Retention templates | As an operator, I can create or update retention message templates. | Template cards show existing/missing state, open create/edit dialog, validate non-empty text, create or update by key, and reload templates. | webapp/src/app/(admin)/admin/broadcast/page.tsx | /api/admin/templates | Copy should preserve POKROV release honesty. | Code inventory | Retested pass | Playwright admin-gate; source-code user-story audit. | PASS 2026-06-26: npx.cmd playwright test e2e/admin-gate.spec.ts (19/19). |  | No fix needed | Passed 2026-06-26
ADM-032 | Admin broadcast | /admin/broadcast | Operator | Live updates | As an operator, I can create, edit, deactivate, or delete backend-owned live update notices. | Live update dialog captures title/summary/link/sort order or active state, persists create/update/delete, reloads rows, and opens links externally. | webapp/src/app/(admin)/admin/broadcast/page.tsx | /api/admin/live-updates | Dynamic app notices are backend-owned JSON, not arbitrary HTML/JS. | Code inventory | Retested pass | Playwright admin-gate; source-code user-story audit. | PASS 2026-06-26: npx.cmd playwright test e2e/admin-gate.spec.ts (19/19). |  | No fix needed | Passed 2026-06-26
ADM-033 | Admin tickets | /admin/tickets | Operator | Ticket queue triage | As an operator, I can filter support tickets, select a ticket, and inspect the conversation. | Tickets page filters by status, loads up to 80 tickets, preserves/chooses selection, shows empty states, and renders messages with sender/status metadata. | webapp/src/app/(admin)/admin/tickets/page.tsx | /api/admin/tickets | Web admin is primary support surface; Telegram support is fallback-only. | E2E exists: admin-gate | Retested pass | Playwright admin-gate; source-code user-story audit. | PASS 2026-06-26: npx.cmd playwright test e2e/admin-gate.spec.ts (19/19). |  | No fix needed | Passed 2026-06-26
ADM-034 | Admin tickets | /admin/tickets | Operator | Ticket reply and status | As an operator, I can insert reply macros, send replies, use Ctrl/Cmd+Enter, and update ticket status. | Reply requires non-empty body, macros append text, status buttons call stable API status codes, updates replace selected ticket, and reply clears after success. | webapp/src/app/(admin)/admin/tickets/page.tsx | /api/admin/tickets/{id}/reply; /api/admin/tickets/{id}/status | Support lifecycle must be async and auditable. | E2E exists: admin-gate | Retested pass | Playwright admin-gate; source-code user-story audit. | PASS 2026-06-26: npx.cmd playwright test e2e/admin-gate.spec.ts (19/19). |  | No fix needed | Passed 2026-06-26

## Defects
Defect ID | Story IDs | Severity | Type | Source | Observed/Risk | Expected Behavior | Repro/Test | Fix Status | Retest Status | Notes
D-001 | WEB-001 | High | UX / release-gate honesty | Code audit + Playwright | Root email auth UI could render before proving /api/auth/email/status was public-ready. | Email forms stay hidden/degraded unless enabled, public_enabled, delivery_configured, delivery_secret_configured, and debug_echo=false are all true. | npx.cmd playwright test e2e/settings-email-link.spec.ts; cabinet-flow root auth scenarios. | Retested pass | PASS 2026-06-26 | Fixed in webapp/src/components/cabinet-entry-auth.tsx by gating email forms with isEmailAuthPublicReady().
D-002 | WEB-019 | Medium | UX / release-gate honesty | Code audit + Playwright | Settings email linking was available without the same public email readiness gate. | Settings shows email linking only when email delivery is public-ready; otherwise it shows Telegram/support fallback copy. | npx.cmd playwright test e2e/settings-email-link.spec.ts | Retested pass | PASS 2026-06-26 | Fixed in webapp/src/app/(dashboard)/settings/page.tsx; added blocked-delivery regression.
D-003 | WEB-013 | Medium | UX / logistics | Code audit + Playwright | A direct /subscription/#manual-setup hash could open manual fallback controls when no subscription URL/access was available. | Manual QR/copy/open controls stay unavailable until manualAccessReady is true, including direct hash entry. | npx.cmd playwright test e2e/cabinet-flow.spec.ts | Retested pass | PASS 2026-06-26 | Fixed in webapp/src/app/(dashboard)/subscription/page.tsx; regression covers direct hash with no active link.
D-004 | WEB-005 | Low | Test / logistics | Playwright failure | OIDC fallback test targeted an old Telegram CTA label and failed although the current UI used 'Войти через Telegram'. | The test should verify the OIDC fallback against the current Telegram login CTA. | npx.cmd playwright test e2e/oidc-fallback.spec.ts e2e/telegram-login-refresh.spec.ts | Retested pass | PASS 2026-06-26 | Fixed in webapp/e2e/oidc-fallback.spec.ts by matching the current Telegram CTA.
D-005 | WEB-001; WEB-019; WEB-020 | Low | Test / logistics | Playwright failure | Settings/email tests depended on the live Telegram WebApp script; a first stub omitted onEvent/offEvent and triggered a runtime error. | Browser tests should stub Telegram WebApp methods used by the app and avoid external-script timeouts. | npx.cmd playwright test e2e/settings-email-link.spec.ts | Retested pass | PASS 2026-06-26 | Fixed in webapp/e2e/settings-email-link.spec.ts with a deterministic Telegram WebApp stub.

## Test Runs
Run ID | Date | Tool/Command | Scope | Result | Evidence | Notes
TR-000 | 2026-06-26 | Code inventory | All webapp routes/components/API calls/e2e names | PASS | 58 source-derived user stories, route inventory, source notes, and expected behaviors recorded. | Initial workbook creation completed before browser test loop.
TR-001 | 2026-06-26 | npm.cmd run build | Next.js build, TypeScript, static route generation | PASS | Build compiled successfully; 34 static routes generated. | Ran after UI fixes and again after test-harness updates.
TR-002 | 2026-06-26 | npx.cmd playwright test e2e/settings-email-link.spec.ts e2e/oidc-fallback.spec.ts e2e/telegram-login-refresh.spec.ts | Initial auth/settings retest loop | FAIL | 12/13 passed; settings blocked-delivery regression hung on live Telegram script before session loading. | Logged as D-005; followed by deterministic Telegram WebApp stub.
TR-003 | 2026-06-26 | npx.cmd playwright test e2e/settings-email-link.spec.ts | Root email auth, settings email link, blocked delivery gate, Telegram linking | PASS | 6/6 passed. | Confirms D-001, D-002, and D-005 fixes.
TR-004 | 2026-06-26 | npx.cmd playwright test e2e/oidc-fallback.spec.ts e2e/telegram-login-refresh.spec.ts | Telegram OIDC fallback and stale-login refresh helpers | PASS | 7/7 passed. | Confirms D-004 fix.
TR-005 | 2026-06-26 | npx.cmd playwright test e2e/cabinet-flow.spec.ts | Cabinet user stories, mobile layout, subscription/manual setup, support, downloads | PASS | 27/27 passed. | Confirms D-003 and broad cabinet retest.
TR-006 | 2026-06-26 | npx.cmd playwright test e2e/admin-gate.spec.ts | Admin/operator user stories | PASS | 19/19 passed. | Admin routing, release cockpit, users, nodes, network, broadcast, tickets, and payments retested.

## Route Inventory
Route | Feature | Primary Source | Behavior Notes
/ | Cabinet auth entry | webapp/src/app/page.tsx | Root entry/auth; redirects valid sessions to /dashboard/.
/verify | Email verify bridge | webapp/src/app/verify/page.tsx | Redirects verification token into root auth.
/recover | Email recovery bridge | webapp/src/app/recover/page.tsx | Redirects recovery token into root auth.
/pricing | Compatibility redirect | webapp/src/app/pricing/page.tsx | Redirects to /subscription/.
/dashboard/ | Cabinet dashboard | webapp/src/app/(dashboard)/dashboard/page.tsx | Access status and summary.
/downloads/ | Downloads | webapp/src/app/(dashboard)/downloads/page.tsx | Client app downloads.
/dashboard/downloads/ | Compatibility redirect | webapp/src/app/(dashboard)/dashboard/downloads/page.tsx | Redirects to /downloads/.
/devices/ | Devices | webapp/src/app/(dashboard)/devices/page.tsx | Device/runtime summary.
/statistics/ | Statistics | webapp/src/app/(dashboard)/statistics/page.tsx | Safe usage summary.
/redeem/ | Redeem | webapp/src/app/(dashboard)/redeem/page.tsx | Access key/gift/promo activation.
/settings/ | Settings | webapp/src/app/(dashboard)/settings/page.tsx | Identity, Telegram, email, bonus settings.
/profile/ | Compatibility redirect | webapp/src/app/(dashboard)/profile/page.tsx | Redirects to /settings/.
/subscription/ | Subscription | webapp/src/app/(dashboard)/subscription/page.tsx | Plans and manual setup fallback.
/subscription/checkout/ | Checkout | webapp/src/app/(dashboard)/subscription/checkout/page.tsx | RUB checkout continuation.
/support/ | Support | webapp/src/app/(dashboard)/support/page.tsx | Tickets and support actions.
/support/thread/ | Support thread | webapp/src/app/(dashboard)/support/thread/page.tsx | Ticket conversation.
/support/legal/ | Legal support | webapp/src/app/(dashboard)/support/legal/page.tsx | Offer/privacy links.
/admin | Admin redirect | webapp/src/app/(admin)/admin/page.tsx | Redirects to /admin/dashboard.
/admin/dashboard | Admin dashboard | webapp/src/app/(admin)/admin/dashboard/page.tsx | Operator shift summary.
/admin/funnel | Admin funnel | webapp/src/app/(admin)/admin/funnel/page.tsx | Conversion diagnostics.
/admin/release | Release cockpit | webapp/src/app/(admin)/admin/release/page.tsx | Beta gate/status surface.
/admin/users | Users | webapp/src/app/(admin)/admin/users/page.tsx | User search/detail/actions.
/admin/bonuses | Bonuses | webapp/src/app/(admin)/admin/bonuses/page.tsx | Wheel and loyalty config.
/admin/referrals | Referrals | webapp/src/app/(admin)/admin/referrals/page.tsx | Start links, campaign links, referral queue.
/admin/promos | Promos | webapp/src/app/(admin)/admin/promos/page.tsx | Access keys and promo slots.
/admin/payments | Payments | webapp/src/app/(admin)/admin/payments/page.tsx | Ledger and manual reconciliation.
/admin/nodes | Nodes | webapp/src/app/(admin)/admin/nodes/page.tsx | Health, metrics, drift, node actions.
/admin/network | Network | webapp/src/app/(admin)/admin/network/page.tsx | Network rollout JSON config.
/admin/broadcast | Broadcast | webapp/src/app/(admin)/admin/broadcast/page.tsx | Broadcasts, templates, live updates.
/admin/tickets | Admin tickets | webapp/src/app/(admin)/admin/tickets/page.tsx | Ticket triage/reply/status.

## Source Notes
Source | Role in tracker
AGENTS.md user prompt | Repository canon and release-gate rules.
docs/README.md | Docs index.
docs/product/portal-vpn-product.md | Product facts, positioning, trial/reward/payment truth.
docs/architecture/system-overview.md | Backend/web/admin architecture and operating model.
docs/architecture/app-first-and-bonus-flows.md | App-first session, Telegram, bonus, and node-pool rules.
docs/operations/deployment-and-access.md | Deployment, release, and access boundaries.
docs/operations/monitoring-and-visibility.md | Telemetry, node health, origin checks.
docs/developer/developer-guide.md | Local workflow and test guidance.
docs/developer/repository-map.md | Repository ownership map.
webapp/README.md | Webapp-specific commands and surface definition.
webapp/src/app/**; webapp/src/components/**; webapp/src/lib/api.ts | Code-derived behavior source.
webapp/e2e/*.spec.ts | Existing executable coverage and expected behaviors.