## Summary
POKROV Marketing Landing User Story Tracker
Goal ID | 019f05ac-5b2e-7053-abc2-f4ac146e2ff4 | Status | Count
Created | 2026-06-26 | Ready for testing | 0
Scope | marketing web landing routes, checkout, install, legal, machine-readable surfaces, responsive/copy guardrails | Pass | 0
Canonical Tracker | C:/Users/kiwun/Documents/ai/VPN/outputs/019f05ac-5b2e-7053-abc2-f4ac146e2ff4/marketing_landing_user_story_tracker.xlsx | Fail | 0
Story Count | 55 | Fixed - retest pending | 0
Current Phase | Retest complete; all 55 stories are Retest pass | Retest pass | 55
|  | Blocked | 0
|  | Not requested | 0

## User Stories
ID | Surface | Route | Feature | User Story | Expected Behavior Based On Code | Evidence Source | Priority | Test Type | Current Status | First Test Result | Errors / Observations | Fix Applied | Retest Result | Notes
ML-001 | Home | / | Home route metadata and structured data | As a search or social visitor, I want the home page to expose canonical metadata and product facts so that previews and indexing represent POKROV accurately. | The home page uses buildMarketingMetadata with canonical / and Russian title/description, root layout emits global Organization/WebSite JSON-LD, and the home component emits SoftwareApplication and FAQ JSON-LD. | marketing/src/app/page.tsx; marketing/src/app/layout.tsx; marketing/src/components/home/homepage.tsx; marketing/src/lib/marketing-site.ts | P0 | Source + browser metadata | Retest pass | Pass in first browser/source pass. |  |  | Pass: post-fix build, responsive, browser, or source guardrail coverage remained green. | No logistical or UX defect found for this story.
ML-002 | Home | / | Topbar brand home link | As a visitor, I want the POKROV mark in the topbar to return me to the home page. | The topbar renders MarketingBrandLogo and the POKROV wordmark inside a Next Link to /. | marketing/src/components/home/homepage-topbar.tsx | P1 | Browser interaction | Retest pass | Pass in first browser/source pass. |  |  | Pass: post-fix build, responsive, browser, or source guardrail coverage remained green. | No logistical or UX defect found for this story.
ML-003 | Home | / | Desktop section navigation | As a visitor scanning the page, I want top navigation links that jump to the major sections. | Desktop nav exposes anchors #features, #how-it-works, #pricing, and #faq with aria-label navigation. | marketing/src/components/home/homepage-topbar.tsx; marketing/src/components/home/homepage.tsx | P1 | Browser interaction | Retest pass | Pass in first browser/source pass. |  |  | Pass: post-fix build, responsive, browser, or source guardrail coverage remained green. | No logistical or UX defect found for this story.
ML-004 | Home | / | Topbar cabinet link | As an existing user, I want a clear path from the marketing home page to my cabinet. | The desktop topbar renders an external cabinet href from getPokrovPublicConfig().webappUrl and opens it in the same tab. | marketing/src/components/home/homepage.tsx; marketing/src/components/home/homepage-topbar.tsx; shared/public-urls.json | P1 | Browser link audit | Retest pass | Pass in first browser/source pass. |  |  | Pass: post-fix build, responsive, browser, or source guardrail coverage remained green. | No logistical or UX defect found for this story.
ML-005 | Home | / | Topbar install CTA | As a new visitor, I want the primary topbar action to start installation rather than checkout. | The primary topbar CTA points to /install/ and is labeled for starting free access. | marketing/src/components/home/homepage.tsx; marketing/src/components/home/homepage-topbar.tsx | P0 | Browser link audit | Retest pass | Pass in first browser/source pass. |  |  | Pass: post-fix build, responsive, browser, or source guardrail coverage remained green. | No logistical or UX defect found for this story.
ML-006 | Home | / | Mobile menu open state | As a mobile visitor, I want a menu button that opens a full menu without shifting the page unexpectedly. | At mobile widths the menu button sets open=true, the dialog overlay gets data-open=true, aria-expanded reflects state, and body overflow is locked while open. | marketing/src/components/home/homepage-topbar.tsx; marketing/src/components/home/homepage.module.css | P0 | Browser interaction | Retest pass | Pass in first browser/source pass. |  |  | Pass: post-fix build, responsive, browser, or source guardrail coverage remained green. | No logistical or UX defect found for this story.
ML-007 | Home | / | Mobile menu close paths | As a mobile visitor, I want to close the menu by using Escape, the close button, backdrop, or a menu link. | Escape, close button, overlay click, nav links, install link, and cabinet link all call setOpen(false), and the prior body overflow value is restored. | marketing/src/components/home/homepage-topbar.tsx | P0 | Browser interaction | Retest pass | Pass in first browser/source pass. |  |  | Pass: post-fix build, responsive, browser, or source guardrail coverage remained green. | No logistical or UX defect found for this story.
ML-008 | Home | / | Hero primary CTA | As a first-time visitor, I want the hero primary action to start the app-first installation flow. | The hero primary Link uses links.installHref, which is /install/. | marketing/src/components/home/homepage.tsx | P0 | Browser link audit | Retest pass | Pass in first browser/source pass. |  |  | Pass: post-fix build, responsive, browser, or source guardrail coverage remained green. | No logistical or UX defect found for this story.
ML-009 | Home | / | Hero secondary CTA | As a cautious visitor, I want the hero secondary action to explain the flow before I install. | The hero secondary anchor points to #how-it-works. | marketing/src/components/home/homepage.tsx | P1 | Browser interaction | Retest pass | Fail: release-readiness test expected the old #pricing hero secondary anchor. | D-001: stale test assertion contradicted current code/user-story behavior (#how-it-works). | Updated tests/test_marketing_release_readiness.py to assert #how-it-works. | Pass: focused pytest suite passed after fix. | Browser source-accurate check also passed for #how-it-works.
ML-010 | Home | / | Hero trust facts | As a visitor comparing the offer, I want quick facts about trial, price, platforms, and devices. | The TRUST array renders four facts: 5-day trial, from 99 RUB, Android + Windows, and up to 5 devices. | marketing/src/components/home/homepage.tsx; shared/product-facts.json; shared/tariff-catalog.json | P1 | Browser content | Retest pass | Pass in first browser/source pass. |  |  | Pass: post-fix build, responsive, browser, or source guardrail coverage remained green. | No logistical or UX defect found for this story.
ML-011 | Home | / | Hero app preview | As a visitor, I want the hero visual to show what the app state looks like before I commit. | HeroAppPreview renders POKROV, protected and connected status, automatic best route, platform chips, and a current connection block. | marketing/src/components/home/homepage.tsx; marketing/src/components/home/homepage.module.css | P2 | Browser visual | Retest pass | Pass in first browser/source pass. |  |  | Pass: post-fix build, responsive, browser, or source guardrail coverage remained green. | No logistical or UX defect found for this story.
ML-012 | Home | / | Feature cards | As a visitor, I want a concise list of what the service does. | The FEATURES array renders four benefit cards covering service access, one-tap connect, Android/Windows/cabinet, and support plus Telegram bonus. | marketing/src/components/home/homepage.tsx | P1 | Browser content | Retest pass | Pass in first browser/source pass. |  |  | Pass: post-fix build, responsive, browser, or source guardrail coverage remained green. | No logistical or UX defect found for this story.
ML-013 | Home | / | Reveal animation safety | As a visitor with slow JavaScript or reduced motion, I want content to remain visible. | Reveal starts visible, only hides after IntersectionObserver is available, marks items visible on intersection, and respects reduced motion/no-JS fallback styles. | marketing/src/components/home/reveal.tsx; marketing/src/components/home/homepage.module.css | P1 | Source + browser content | Retest pass | Pass after source-accurate scroll check. | Full-page screenshot captured off-screen reveal sections before scroll; not a user-facing failure. | No product code change required. | Pass: after scrolling to features, wrapper/card opacity was effectively 1. | Reveal implementation remains SSR/no-JS/reduced-motion safe by source inspection.
ML-014 | Home | / | App flow showcase | As a visitor, I want to see the app flow before installing. | The showcase renders three phone panels for connect, location, and access with stable labels and visual states. | marketing/src/components/home/homepage.tsx; marketing/src/components/home/homepage.module.css | P2 | Browser visual | Retest pass | Pass in first browser/source pass. |  |  | Pass: post-fix build, responsive, browser, or source guardrail coverage remained green. | No logistical or UX defect found for this story.
ML-015 | Home | / | How-it-works steps | As a new user, I want to understand the path from install to paid continuation. | The HOW_IT_WORKS array renders four ordered steps: install, enter app, connect, continue from cabinet or checkout. | marketing/src/components/home/homepage.tsx | P1 | Browser content | Retest pass | Pass in first browser/source pass. |  |  | Pass: post-fix build, responsive, browser, or source guardrail coverage remained green. | No logistical or UX defect found for this story.
ML-016 | Home | / | Pricing plan eligibility | As a buyer, I want only checkout-ready plans shown on the landing page. | buildPlanCards filters active tariff plans to CHECKOUT_READY_PLAN_CODES, currently only start_99. | marketing/src/components/home/homepage.tsx; shared/tariff-catalog.json | P0 | Source + browser content | Retest pass | Pass in first browser/source pass. |  |  | Pass: post-fix build, responsive, browser, or source guardrail coverage remained green. | No logistical or UX defect found for this story.
ML-017 | Home | / | Pricing checkout CTA | As a buyer with intent, I want the pricing CTA to open checkout for the shown plan. | Each pricing card CTA links to /checkout/?plan=start_99 using buildCheckoutHref. | marketing/src/components/home/homepage.tsx | P0 | Browser link audit | Retest pass | Pass in first browser/source pass. |  |  | Pass: post-fix build, responsive, browser, or source guardrail coverage remained green. | No logistical or UX defect found for this story.
ML-018 | Home | / | FAQ section | As a visitor with common objections, I want visible answers without leaving the page. | FaqSection renders code-defined MARKETING_FAQ items using native details/summary semantics and has id=faq. | marketing/src/components/home/homepage.tsx; marketing/src/lib/marketing-site.ts | P1 | Browser interaction | Retest pass | Pass in first browser/source pass. |  |  | Pass: post-fix build, responsive, browser, or source guardrail coverage remained green. | No logistical or UX defect found for this story.
ML-019 | Home | / | Final CTA split | As a visitor reaching the bottom, I want install as the main action and checkout as the secondary action. | FinalCta primary uses /install/ and secondary uses /checkout/?plan=start_99. | marketing/src/components/home/homepage.tsx | P0 | Browser link audit | Retest pass | Fail: release-readiness test expected the old btnPill final CTA class. | D-001: stale test assertion ignored current final CTA style and install-before-checkout order. | Updated tests/test_marketing_release_readiness.py to assert install appears before checkout and styles.btnLight is used. | Pass: focused pytest suite passed after fix. | Final CTA still exposes install as primary and checkout as secondary.
ML-020 | Home | / | Footer navigation | As a visitor, I want footer links for install, page sections, cabinet, support, news, offer, and privacy. | Footer renders links to /install/, #features, #pricing, app cabinet URL, Telegram support/news URLs, /offer/, and /privacy/. | marketing/src/components/home/homepage.tsx; shared/public-urls.json | P1 | Browser link audit | Retest pass | Pass in first browser/source pass. |  |  | Pass: post-fix build, responsive, browser, or source guardrail coverage remained green. | No logistical or UX defect found for this story.
ML-021 | Scenario landing | /mobile/ | Mobile scenario page | As a mobile-search visitor, I want a route-specific page for phone setup. | The /mobile/ page uses MarketingLanding with mobile title, description, breadcrumbs, scenario cards, FAQ, install CTA, and checkout CTA. | marketing/src/app/mobile/page.tsx; marketing/src/components/marketing-landing.tsx | P1 | Browser content | Retest pass | Pass in first browser/source pass. |  |  | Pass: post-fix build, responsive, browser, or source guardrail coverage remained green. | No logistical or UX defect found for this story.
ML-022 | Scenario landing | /youtube/ | YouTube scenario page | As a visitor looking for YouTube access help, I want page copy that explains the POKROV path honestly. | The /youtube/ page uses MarketingLanding with route-specific metadata, breadcrumbs, install CTA, checkout CTA, FAQ, and related pages. | marketing/src/app/youtube/page.tsx; marketing/src/components/marketing-landing.tsx | P1 | Browser content | Retest pass | Pass in first browser/source pass. |  |  | Pass: post-fix build, responsive, browser, or source guardrail coverage remained green. | No logistical or UX defect found for this story.
ML-023 | Scenario landing | /tiktok/ | TikTok scenario page | As a visitor looking for TikTok access help, I want page copy and actions specific to that scenario. | The /tiktok/ page uses MarketingLanding with TikTok metadata, breadcrumbs, install CTA, checkout CTA, FAQ, and related pages. | marketing/src/app/tiktok/page.tsx; marketing/src/components/marketing-landing.tsx | P1 | Browser content | Retest pass | Pass in first browser/source pass. |  |  | Pass: post-fix build, responsive, browser, or source guardrail coverage remained green. | No logistical or UX defect found for this story.
ML-024 | Scenario landing | /telegram/ | Telegram scenario page | As a visitor focused on Telegram, I want route-specific copy and the same app-first actions. | The /telegram/ page uses MarketingLanding with Telegram metadata, breadcrumbs, install CTA, checkout CTA, FAQ, and related pages. | marketing/src/app/telegram/page.tsx; marketing/src/components/marketing-landing.tsx | P1 | Browser content | Retest pass | Pass in first browser/source pass. |  |  | Pass: post-fix build, responsive, browser, or source guardrail coverage remained green. | No logistical or UX defect found for this story.
ML-025 | Scenario landing | /devices/ | Devices scenario page | As a visitor comparing supported devices, I want route-specific Android and Windows guidance. | The /devices/ page uses MarketingLanding with device metadata, breadcrumbs, install CTA, checkout CTA, FAQ, and related pages. | marketing/src/app/devices/page.tsx; marketing/src/components/marketing-landing.tsx | P1 | Browser content | Retest pass | Pass in first browser/source pass. |  |  | Pass: post-fix build, responsive, browser, or source guardrail coverage remained green. | No logistical or UX defect found for this story.
ML-026 | Scenario landing | /mobile/ /devices/ /youtube/ /tiktok/ /telegram/ | Legacy landing theme toggle | As a visitor on a scenario landing page, I want the theme toggle to switch light and dark without reloading. | MarketingLanding renders a button with data-theme-toggle, and RootLayout's inline script toggles localStorage theme and document data-theme. | marketing/src/components/marketing-landing.tsx; marketing/src/app/layout.tsx; marketing/src/app/globals.css | P2 | Browser interaction | Retest pass | Pass in first browser/source pass. |  |  | Pass: post-fix build, responsive, browser, or source guardrail coverage remained green. | No logistical or UX defect found for this story.
ML-027 | Scenario landing | /mobile/ /devices/ /youtube/ /tiktok/ /telegram/ | Scenario page CTAs | As a visitor on any scenario page, I want install as the main action and checkout as an explicit paid continuation. | MarketingLanding renders install CTA to /install/ and checkout CTA to /checkout/?plan=start_99. | marketing/src/components/marketing-landing.tsx | P0 | Browser link audit | Retest pass | Pass in first browser/source pass. |  |  | Pass: post-fix build, responsive, browser, or source guardrail coverage remained green. | No logistical or UX defect found for this story.
ML-028 | Scenario landing | /mobile/ /devices/ /youtube/ /tiktok/ /telegram/ | Scenario FAQs | As a visitor on a scenario page, I want FAQ answers that expand with native controls. | MarketingLanding renders MARKETING_FAQ items in details/summary elements. | marketing/src/components/marketing-landing.tsx; marketing/src/lib/marketing-site.ts | P1 | Browser interaction | Retest pass | Pass in first browser/source pass. |  |  | Pass: post-fix build, responsive, browser, or source guardrail coverage remained green. | No logistical or UX defect found for this story.
ML-029 | Scenario landing | /mobile/ /devices/ /youtube/ /tiktok/ /telegram/ | Related page cross-links | As a visitor, I want related scenario links that do not point to the page I am already viewing. | MarketingLanding filters related pages by currentPath before rendering related links. | marketing/src/components/marketing-landing.tsx; marketing/src/lib/marketing-site.ts | P2 | Browser link audit | Retest pass | Pass in first browser/source pass. |  |  | Pass: post-fix build, responsive, browser, or source guardrail coverage remained green. | No logistical or UX defect found for this story.
ML-030 | SEO landing | /vpn/ | VPN search-intent copy | As a VPN-search visitor, I want the page to use my search language while staying honest about beta status and fit. | The /vpn/ page visibly uses VPN and Vpn terms for search intent, says POKROV is not best for everyone, and keeps beta/platform claims constrained. | marketing/src/app/vpn/page.tsx; AGENTS.md public wording rule | P0 | Browser content + source guardrail | Retest pass | Pass in first browser/source pass. |  |  | Pass: post-fix build, responsive, browser, or source guardrail coverage remained green. | No logistical or UX defect found for this story.
ML-031 | SEO landing | /vpn/ | VPN metadata and JSON-LD | As a search engine, I want canonical metadata and structured data for the dedicated VPN page. | The /vpn/ page has canonical /vpn/, route-specific keywords, breadcrumbs, Article JSON-LD, and FAQ JSON-LD. | marketing/src/app/vpn/page.tsx; marketing/src/lib/marketing-site.ts | P1 | Source + browser metadata | Retest pass | Pass in first browser/source pass. |  |  | Pass: post-fix build, responsive, browser, or source guardrail coverage remained green. | No logistical or UX defect found for this story.
ML-032 | SEO landing | /vpn/ | VPN page CTAs | As a VPN-search visitor, I want app-first actions without being sent to raw connection endpoints. | The /vpn/ page links to /install/, /checkout/, and app cabinet URLs, and does not use connect.pokrov.space as a public acquisition CTA. | marketing/src/app/vpn/page.tsx; docs/operations/deployment-and-access.md | P0 | Browser link audit + source guardrail | Retest pass | Pass in first browser/source pass. |  |  | Pass: post-fix build, responsive, browser, or source guardrail coverage remained green. | No logistical or UX defect found for this story.
ML-033 | Install | /install/ | Install page noindex metadata | As the operator, I want the install handoff page available to users without becoming an SEO landing. | Install metadata is built with noIndex=true and canonical /install/. | marketing/src/app/install/page.tsx | P1 | Source + browser metadata | Retest pass | Pass in first browser/source pass. |  |  | Pass: post-fix build, responsive, browser, or source guardrail coverage remained green. | No logistical or UX defect found for this story.
ML-034 | Install | /install/ | Platform download handoff | As a user ready to install, I want Android and Windows actions that lead to the safest currently available handoff. | Platform cards link to cabinet downloads when env public binary URLs exist, otherwise they fall back to support/help; copy notes outside-store beta and Windows publisher limitations. | marketing/src/app/install/page.tsx; shared/portal-config.ts | P0 | Browser link audit + content | Retest pass | Pass in first browser/source pass. |  |  | Pass: post-fix build, responsive, browser, or source guardrail coverage remained green. | No logistical or UX defect found for this story.
ML-035 | Install | /install/ | Install support paths | As a user blocked during install, I want obvious cabinet and support options. | Install page renders cabinet and support/news/bot links from public config. | marketing/src/app/install/page.tsx; shared/public-urls.json | P1 | Browser link audit | Retest pass | Pass in first browser/source pass. |  |  | Pass: post-fix build, responsive, browser, or source guardrail coverage remained green. | No logistical or UX defect found for this story.
ML-036 | Checkout | /checkout/?plan=start_99 | Checkout metadata and breadcrumb | As a buyer, I want checkout to load with clear title and breadcrumb context. | Checkout page uses buildMarketingMetadata for /checkout/ and emits Breadcrumb JSON-LD. | marketing/src/app/checkout/page.tsx | P1 | Source + browser metadata | Retest pass | Pass in first browser/source pass. |  |  | Pass: post-fix build, responsive, browser, or source guardrail coverage remained green. | No logistical or UX defect found for this story.
ML-037 | Checkout | /checkout/?plan=start_99 | Checkout plan selection | As a buyer, I want checkout to select a known public plan and avoid unavailable plans. | CheckoutClient starts from URL plan=start_99, uses fallback start_99, and keeps public active plan handling constrained. | marketing/src/app/checkout/checkout-client.tsx; shared/tariff-catalog.json | P0 | Browser interaction | Retest pass | Pass in first browser/source pass. |  |  | Pass: post-fix build, responsive, browser, or source guardrail coverage remained green. | No logistical or UX defect found for this story.
ML-038 | Checkout | /checkout/?plan=start_99 | Checkout API fallback | As a buyer, I want checkout to remain understandable when live payment/catalog APIs are unreachable locally. | CheckoutClient tries candidate API bases for catalog/providers/status, records failure state, and keeps a visible fallback/helper instead of crashing. | marketing/src/app/checkout/checkout-client.tsx | P0 | Browser fallback | Retest pass | Pass with real fallback route smoke and mocked provider-ready checkout smoke. | Initial checkout smoke mocked CORS too broadly; harness issue only. | Adjusted output smoke mock headers; no product code change required. | Pass: mocked checkout smoke reported no failures and no console errors. | Local static route also renders when live API calls are unavailable.
ML-039 | Checkout | /checkout/?plan=start_99 | Access key lookup and redeem | As a user with an existing key, I want checkout to check the key and point me to redeem. | Entering a key calls /api/access-keys/status/:key across candidate bases; successful key state builds a webapp /redeem/?key= link. | marketing/src/app/checkout/checkout-client.tsx | P1 | Browser interaction with mocked network | Retest pass | Pass in mocked checkout interaction smoke. |  |  | Pass: key lookup, promo normalization, email validation, and order redirect were all exercised with mocked API responses. | No live payment/order side effect was performed.
ML-040 | Checkout | /checkout/?plan=start_99 | Promo code handling | As a buyer with a promo code, I want the field to normalize my input and preview the discount. | Promo input uppercases and trims input, getPricingPreviewDiscountPercent computes the preview, and invalid/empty codes do not create a fake discount. | marketing/src/app/checkout/checkout-client.tsx; shared/portal-config.ts | P1 | Browser interaction | Retest pass | Pass in mocked checkout interaction smoke. |  |  | Pass: key lookup, promo normalization, email validation, and order redirect were all exercised with mocked API responses. | No live payment/order side effect was performed.
ML-041 | Checkout | /checkout/?plan=start_99 | Checkout email validation | As a buyer, I want checkout to ask for an email before creating a public order. | If email is blank, create order is blocked client-side and a visible status asks the user to enter email. | marketing/src/app/checkout/checkout-client.tsx | P0 | Browser interaction | Retest pass | Pass in mocked checkout interaction smoke. |  |  | Pass: key lookup, promo normalization, email validation, and order redirect were all exercised with mocked API responses. | No live payment/order side effect was performed.
ML-042 | Checkout | /checkout/?plan=start_99 | Checkout order redirect | As a buyer with valid input, I want checkout to create a payment order and redirect me to the provider. | When payment provider state is ready, CheckoutClient POSTs /api/payments/orders/create-public and redirects to payment_url; if provider is missing/blocked, the button/fallback state prevents a broken order. | marketing/src/app/checkout/checkout-client.tsx | P0 | Browser interaction with mocked network | Retest pass | Pass in mocked checkout interaction smoke. |  |  | Pass: key lookup, promo normalization, email validation, and order redirect were all exercised with mocked API responses. | No live payment/order side effect was performed.
ML-043 | Checkout | /checkout/?plan=start_99 | Checkout helper links | As a buyer needing help, I want checkout to offer redeem, cabinet, bot, and install support paths. | Checkout side/helper links include redeem/cabinet/bot/install destinations built from public config and code helpers. | marketing/src/app/checkout/checkout-client.tsx; shared/public-urls.json | P1 | Browser link audit | Retest pass | Pass in first browser/source pass. |  |  | Pass: post-fix build, responsive, browser, or source guardrail coverage remained green. | No logistical or UX defect found for this story.
ML-044 | Legal | /offer/ | Offer page | As a buyer, I want legal terms and beta limitations before payment. | Offer page renders legal terms, beta limitations, contacts, breadcrumbs, and links to home/install/privacy/cabinet/support without unsupported store/stable claims. | marketing/src/app/offer/page.tsx | P0 | Browser content + link audit | Retest pass | Pass in first browser/source pass. |  |  | Pass: post-fix build, responsive, browser, or source guardrail coverage remained green. | No logistical or UX defect found for this story.
ML-045 | Legal | /privacy/ | Privacy page | As a privacy-conscious visitor, I want to see what data is collected and how to contact support. | Privacy page renders data-use sections, contacts, breadcrumbs, and links to home/install/offer/cabinet/support. | marketing/src/app/privacy/page.tsx | P0 | Browser content + link audit | Retest pass | Pass in first browser/source pass. |  |  | Pass: post-fix build, responsive, browser, or source guardrail coverage remained green. | No logistical or UX defect found for this story.
ML-046 | Machine-readable | /robots.txt | Robots policy | As a crawler, I want robots instructions with sitemap and host. | robots.ts allows public routes, disallows /api/ and /_next/, includes bot-specific rules, sitemap, and canonical host. | marketing/src/app/robots.ts | P1 | HTTP/source | Retest pass | Pass in source/browser/link guardrails. |  |  | Pass: SEO, link, public-copy, and browser machine-route checks passed after fix. | Machine-readable and policy/copy behavior verified without product code changes.
ML-047 | Machine-readable | /sitemap.xml | Sitemap | As a crawler, I want canonical marketing and machine-readable routes in the sitemap. | sitemap.ts returns buildMarketingSitemap entries for canonical pages and machine paths including /llms.txt and /pricing.md. | marketing/src/app/sitemap.ts; marketing/src/lib/marketing-site.ts | P1 | HTTP/source | Retest pass | Pass in source/browser/link guardrails. |  |  | Pass: SEO, link, public-copy, and browser machine-route checks passed after fix. | Machine-readable and policy/copy behavior verified without product code changes.
ML-048 | Machine-readable | /manifest.webmanifest | Web app manifest | As a browser, I want manifest metadata and icons for installability and rich previews. | manifest.ts returns POKROV name/short_name, standalone display, ru-RU language, theme colors, and PNG/SVG icons. | marketing/src/app/manifest.ts; marketing/public | P2 | HTTP/source | Retest pass | Pass in source/browser/link guardrails. |  |  | Pass: SEO, link, public-copy, and browser machine-route checks passed after fix. | Machine-readable and policy/copy behavior verified without product code changes.
ML-049 | Machine-readable | /llms.txt /pricing.md | AI/search machine files | As an AI/search crawler, I want concise product and pricing files that match public product truth. | Public llms.txt and pricing.md exist, are included in sitemap inputs, and reference canonical POKROV surfaces. | marketing/public/llms.txt; marketing/public/pricing.md; marketing/src/lib/marketing-site.ts | P1 | HTTP/content | Retest pass | Pass in source/browser/link guardrails. |  |  | Pass: SEO, link, public-copy, and browser machine-route checks passed after fix. | Machine-readable and policy/copy behavior verified without product code changes.
ML-050 | Redirects | Legacy SEO paths | Legacy path redirects | As a visitor using an old SEO link, I want to land on the current canonical page. | marketing/public/_redirects maps old mobile, tiktok, youtube, devices, telegram, and vpn variants to current canonical routes with 301! | marketing/public/_redirects; marketing/scripts/check-marketing-seo.mjs | P1 | Source guardrail | Retest pass | Pass in source/browser/link guardrails. |  |  | Pass: SEO, link, public-copy, and browser machine-route checks passed after fix. | Machine-readable and policy/copy behavior verified without product code changes.
ML-051 | Accessibility | All pages | Skip link and main landmark | As a keyboard user, I want to skip repetitive navigation and land on main content. | RootLayout renders a skip link to #main-content and wraps children in main id=main-content. | marketing/src/app/layout.tsx; marketing/src/app/globals.css | P0 | Browser accessibility | Retest pass | Pass in first browser/source pass. |  |  | Pass: post-fix build, responsive, browser, or source guardrail coverage remained green. | No logistical or UX defect found for this story.
ML-052 | Telemetry | All pages | Funnel tracker | As the operator, I want page-view funnel tracking that does not block rendering. | RootLayout includes FunnelTracker in the body after main content; page rendering must still work if tracking fails. | marketing/src/app/layout.tsx; marketing/src/components/funnel-tracker.tsx | P2 | Source + browser console | Retest pass | Pass in first browser/source pass. |  |  | Pass: post-fix build, responsive, browser, or source guardrail coverage remained green. | No logistical or UX defect found for this story.
ML-053 | Responsive | / /mobile/ /devices/ /telegram/ /youtube/ /tiktok/ /vpn/ | Responsive route smoke | As a mobile, tablet, or desktop visitor, I want the landing pages to render without horizontal overflow or framework errors. | check-marketing-responsive validates core routes at mobile, tablet, and desktop for successful response, brand body text, primary CTA, no overlay, and no horizontal overflow. | marketing/scripts/check-marketing-responsive.mjs | P0 | Automated browser smoke | Retest pass | Pass in responsive smoke and browser checks. |  |  | Pass: npm run check:responsive passed after fix. | Responsive smoke covered home and scenario/SEO routes at mobile, tablet, and desktop.
ML-054 | Assets | All pages | Public preview and icon assets | As a browser or social crawler, I want favicon, tab icon, apple icon, and OG/Twitter images to resolve. | Root metadata references existing files in marketing/public for icons, opengraph image, and twitter image. | marketing/src/app/layout.tsx; marketing/public | P1 | Source + HTTP | Retest pass | Pass in source/browser/link guardrails. |  |  | Pass: SEO, link, public-copy, and browser machine-route checks passed after fix. | Machine-readable and policy/copy behavior verified without product code changes.
ML-055 | Policy/copy | Public landing routes | Public copy guardrails | As the owner, I want public landing copy to follow current POKROV wording and release-gate honesty. | Public copy avoids stale POKROV Network wording, hidden/cloaked stuffing, unsupported best/store/stable claims, direct connect acquisition CTAs, and keeps visible VPN usage limited to approved search-intent surfaces. | AGENTS.md; tests/test_public_copy_guardrails.py; tests/test_marketing_release_readiness.py; scripts/check-links.py | P0 | Automated source guardrail | Retest pass | Pass in source/browser/link guardrails. |  |  | Pass: SEO, link, public-copy, and browser machine-route checks passed after fix. | Machine-readable and policy/copy behavior verified without product code changes.

## Test Runs
Run ID | Date | Phase | Command / Tool | Scope | Result | Notes
RUN-001 | 2026-06-26 | Inventory | Source review | All landing, install, checkout, legal, machine-readable, responsive, and copy surfaces | Complete | 55 user stories generated from current code.
RUN-002 | 2026-06-26 | First test | npm.cmd run check:seo | Marketing SEO and redirects | Pass | Marketing SEO/brand checks passed.
RUN-003 | 2026-06-26 | First test | python -m pytest tests/test_marketing_release_readiness.py tests/test_public_copy_guardrails.py tests/test_frontend_text_integrity.py -q | Release/copy/text guardrails | Fail | D-001: stale release-readiness assertion expected #pricing and btnPill.
RUN-004 | 2026-06-26 | First test | python scripts/check-links.py --report outputs/.../link-check-report.md | CTA, metadata, legal, checkout, connect-host guardrails | Pass | Link check passed.
RUN-005 | 2026-06-26 | First test | python scripts/ui_visual_smoke.py --report outputs/.../ui-visual-smoke-report.md | Source-based visual contract smoke | Pass | UI visual smoke passed.
RUN-006 | 2026-06-26 | First test | npm.cmd run build | Marketing production export | Pass after isolated rerun | Parallel build + responsive dev-server run caused a transient .next collision; isolated build passed.
RUN-007 | 2026-06-26 | First test | npm.cmd run check:responsive | Home/scenario/SEO routes across mobile/tablet/desktop | Pass | Responsive checks passed.
RUN-008 | 2026-06-26 | First test | In-app browser QA + refined checks | Home, mobile menu, FAQ, theme toggle, install, checkout fallback, legal, machine routes | Pass | Initial checker had stale text assumptions; source-accurate rerun passed. Reveal scroll opacity verified.
RUN-009 | 2026-06-26 | First test | checkout_mock_smoke.mjs | Checkout key/promo/email/order behavior with mocked API | Pass | No live payment or order side effect; final mock run had no console errors.
RUN-010 | 2026-06-26 | Fix | apply_patch | tests/test_marketing_release_readiness.py | Applied | Updated stale hero/final CTA assertions to current code contract.
RUN-011 | 2026-06-26 | Retest | python -m pytest tests/test_marketing_release_readiness.py tests/test_public_copy_guardrails.py tests/test_frontend_text_integrity.py -q | Release/copy/text guardrails | Pass | 19 passed. Pytest emitted a Windows temp cleanup warning after success.
RUN-012 | 2026-06-26 | Retest | npm.cmd run check:seo; npm.cmd run build; npm.cmd run check:responsive | Marketing SEO, production export, responsive routes | Pass | All three passed after fix.
RUN-013 | 2026-06-26 | Retest | check-links, ui_visual_smoke, checkout_mock_smoke | Links, visual contract, checkout behaviors | Pass | All passed after fix; checkout mock had no console errors.

## Defect Log
Defect ID | Story ID | Severity | Finding | Repro / Command | Status | Fix Applied | Retest Result
D-001 | ML-009; ML-019 | P2 logistical | Release-readiness test still expected the previous hero secondary #pricing anchor and old btnPill final CTA class, while current code and story contract use #how-it-works and btnLight with install before checkout. | python -m pytest tests/test_marketing_release_readiness.py tests/test_public_copy_guardrails.py tests/test_frontend_text_integrity.py -q | Fixed | Updated tests/test_marketing_release_readiness.py to assert #how-it-works, install-before-checkout order, and styles.btnLight. | Pass: focused pytest suite passed 19/19 after fix.